## Sheet1
# | item | Description | PIC | Developer | Status | Remarks | Baseline due date | Revised Baseline due date | Complition Date
1 | Process understanding | Scoping of the process will be performed to understand the feasibility of automation. | Yap Shang Shin |  | Done |  | 11/9/2023 | 2023-09-11
2 | Process Video | It helps to better understand the process. We can see How the user does the manual task. | Yap Shang Shin |  | Done |  | 04/9/2023 | 2023-09-04
3 | Flowchart Creation | We capture the AS-IS process with the help of the user team | Yap Shang Shin |  | Done |  | 04/9/2023 | 2023-09-04
4 | Flowchart Confirmation | The user team approved the flowchart | Yap Shang Shin |  | Done |  | 04/9/2023 | 2023-09-04
5 | PDD Creation | Assess functional requirements and perform in-depth analysis of the process. Prepare Process design document. | Yap Shang Shin |  | Done |  | 04/9/2023 | 2023-09-04
6 | PDD Sign-off | The user team goes through, reviews, and approves documents. After that, all stakeholders give the sign-off. |  |  | pending
7 | SDD Creation | The solution design document describes how to implement the automated solution |  |  | Pending | After compliton of development will share the sdd
8 | SDD Sign-off | All stakeholders need to give the sign of the SDD |  |  | Pending
7 | Test Data | Test Data will be required for use in Development |  |  | Done |  | 2023-09-14
8 | Development Environment Confirmation | The user team needs to notify which module of the system needs to be accessed. The user team shares the test credentials if it is required. |  |  | Pending |  | 2023-09-15
9 | Development | Develop the automation, Build bots for respective applications, Unit test the bots. |  |  | in-progress | Actual development in progress | 2023-10-05
| Development Sub Process 1: Login To LS System, Download Retail Vendor List, Item Status Link, Item Master List and Replen. Item Quanlity Files. | Login the LS system, Download all required files, give proper filter and get the excel |  |  | Development Done, Pending for UAT | BOT Installation on user computer done.
| Development Sub Process 2: Get Promotion File for Combining Data. Prepare Uploading Excel Sheet to LS System. | Promotion file from Merchandising Department on a shared folder, updated Staff Directory on the shared folder and all Downloaded Files form the LS system. Combining all files with proper logic and calculations,prepare the sheet for uploading to the system |  |  | Development done , Fixing some exceptions raised at User End | BOT Installation on user computer done.User is checking with different files data to on LS System.
| Sub Processs 1 & 2 Sign Off From User | The User team needs to sign-off the sub process result after accessing the result. They manually check the result and give sign-off upon everything is ok. |  |  | After Exception handled from My end UAT Sign OFF will Done
| Development Sub Process 3: Upload all the from the Excel Sheet to LS sytem. | This process uploads all the data into the LS system from the signed-off excel file. |  |  | In progress with LS data. Exception raised on some data which was not handled during development. Finishing those. | Bot Installation done.
10 | SIT | Integrate code and perform, System integration testing. |  |  |  |  | 2023-10-10
11 | SIT Sign-off | User give the sign-off |  |  |  |  | 2023-10-10
12 | UAT | End-to-end testing done by the User team. In case of any major defect detected, that need to be fixed |  |  | In progress |  | 2023-10-11
13 | UAT Sign-off | User team provide the sign-off |  |  |  |  | 2023-10-12
14 | Production Implementation | The process will be implemented in a live environment. |  |  | In progress |  | 2023-10-17
15 | Production Implementation sign-off | User team provides the sign-off |  |  |  |  | 2023-10-18
15 | Deployment | Deployment of Bot on Live environment |  |  |  |  | 2023-10-20
16 | Knowledge Transfer | Users will be trained on how to trigger the Bot and maintain configuration files |  |  |  |  | 2023-10-21