## Sprint 21 10.10 - 21.10 (hidden)
| Product Backlog (To Do) | IN PROGRESS |  |  | KIV | KIV Archives
COE RPA | Sprint Goal | Activity & Timeline | In-Progress & Status | DONE | Obstacles & Status of Obstacles
Khoon Yong | GTAC Slide (Centralize shared drive) - To conclude draft slide | Preparation: 22/03/22 - 01/04/22 Review: 04/04/22 - 20/04/22 Presentation: 21/04/22 12/05/22 26/05/22 21/07/22 25/08/22 08/09/22 | Presentation - Done GTAC KIV this paper, GTAC to access on the following items: Once pending items done, email GTacSecteriat to get approval. IT security assessment - 18/10 | Stage 3 template identified - 28/03/22 Completed for Option A - 29/04/22 Dicussion with Rohayah on the 2 options, suggest to go for Option A. - 19/7/22 Discussed with LH, only Option A is anough for GTAC slide presentation - 20/7/22 Rohayah to provide costing for UAT environment (to get the lowest price as possible for Option A -Active Passive) -27/7/22 Seek GTAC committee to review the slide, 2pm. - 24/8/22 Rework on the comment by Poh Ling - 29/08/22 Register for presentation on 08/09 - 30/8 To dicuss with LH on the next step - 9/9 GTAC KIV this paper, GTAC to access on the following items: Is it worth to spend half millions for the dedicated storage. To held a meeting with Infra team to understand more, is there a way from infra team to provide a dedicated storage for RPA. - 14/9 To have further understanding on the product through vendor - 30/9 To come out with the actual usage of the shared drive for RPA. - 5/10 IGS to come out with update Quotation with x1.8TB - 13/10
Khoon Yong | Best Practice knowledge Sharing/ Mandays estimation for processes | Identify process: 13/06/22 | Mandays Sharing process - Completed Best practice sharing - Completed Share the slide(part 4)to the team - 12/10 13/10 14/10 | Mandays estimation - 13/6 Mandays estimation by module - 15/6 First sharing session completed by Janani - 20/6 Mandays estimation sharing - 30/6 To add the items by Mingkin and CO shared on 27/7/22 - 10/8/22 Share the slide (part1) to the team - 16/8/22 Share the slide(part 2)to the team -28/9/22 Share the slide(part 3)to the team - 5/10
Khoon Yong | UiPath Upgrade | Discussion (internal): 13/7/22 Discussion (KGISL): 18/7/22 19/7/22 -KGISL provide service during installation. - Apr 2023 -New hardware needed during upgrade. - Feb 2023 -UiPath to provide extra license during upgrade. - Apr 2023 -Developer to perform testing and fix. Apr 2023 - Jun 2023 | UiPath Version upgrade in progress Uipath to conduct presentation for Test Suite and also Automation Suite - 13/10 17/10 | Discussion with Nic- 14/7/22 Discussion with KGISL - 19/7/22 (4pm) Discussion with KGISL - 9/8/22 (3pm) Email sent to UiPath on the server spec questions and UiPath upgrade queries - 16/8/22 Pending UiPath to revert on the email - 18/8/22 To come out with the slide for architecture go through with Thomasz- 19/8 Tomasz feedback on the architecture - 25/8/22 Cost estimation - 1/9 What approval needed for extension -GCRC- 20/9 Are we getting a lot of support or not - No Jasbir to provide Exception Memo - 27/9 Dicussion with UiPath still in progress Jasbir provided the exception memo, to fill up and submit but need to make sure security patch will be provided. - 7/10 |  |  | 16/06/2022
Khoon Yong | Unable to load log | Unable to load log - These are some common performance delays related to your Orchestrator server or Network or SQL server performance. - If possible please validate the performance and disk space in the orchestrator server and SQL server with your IT team.- 16/8/22 - If possible please share with us the event viewer logs of your Orchestrator server. - 15/8/22 - This happens even if the database tables have more records than expected since we recommend only maintaining less than 2 million records in each table. Can you please run the below command in your database and share the result with us? - 17/8/22 | Action items: Uipath came back with the docs but it is from uipath site. To discuss about this one on elastics (kibana)search with Ikram. TO have meeting with Ikram on 13/10 14/10 | To get the event vier logs of Orchestrator server. - 15/8/22 To log the issue to careline to validate the performance and disk space in the orchestrator and SQL server. -17/8/22 To get the careline to help to data extraction - 17/8/22 Email follow up with careline on the ticket. - 1/9/22 Log case to uipath - 6/9 Uipath need a schedule from us for 3 slots to meet up with them , pending Chee Onn to provide - 9/9 Meet up with UiPath Support team at 3pm - 12/9 Jalilah to provide event viewer log - 13/9 DBA to provide SQL result - 21/9 Ticket create again and pending meet up for further discussion - 23/9 10am Second meet up with uipath support on 27/9.
Khoon Yong | Timeout issue | Timeout issue - when do you see the error? please specify the in details of the steps of your operation. - 15/8/22 - share some screenshot of the error? - 15/8/22 - share the event viewer log - 15/8/22 | Action items: Apply fixes Timeout issue resolved for CDD ODD. Pending : Payment Voucher and Email Trade. | To provide screenshot, to specify details of operations - 15/8/22 To get the event viewer logs of Orchestrator server. - 15/8/22 Log issue to UiPath - 16/8/22 Pending UiPath support to revert - 16/8 To work with UiPath through call to sort it out. -19/8 Uipath time_out changed to 180 instead of 120 Issue reopened on 25/8/22. Uipath Ryan routed this to his internal team - 30/8 Ryan came back with the solution to : 1.add some delay in your process when adding transaction items to queue - Apply in prod, monitoring in progress. Which bot ? BOT24 and BOT25 2.try to include the transition activities in retry scope leave the condition as empty and include the retry interval (Ex : 20 seconds) with retry 3 Timeout issue resolved. To apply changes to the rest of the impacted bot. - 22/9
Khoon Yong | BDS setup for new 6 VDI for UAT2 [Core banking upgrade project] | BDS setup for new 6 VDI for UAT2 BDS installation - 19/9 Chi Chung to provide the schedule next week - 4/10 14/10 | BDS installation - In progress Careline continue the installation - connection issue: Advice from BDS team, to check with Wintel team again on the connection issue - 11/10 14/10 | Working with careline for BDS installation - 19/9 To work with Chi Chung to solve the issue, meet up MA and Careline - 26/9 To work with VDI team on the issue - 27/9 Issue escalated to some parties, to continue work on th issue - 28/9 Wintel team work on it - 30/9 Raised firewall release request - 4/10
Khoon Yong | VPN request for new contract staff | VPN request for new contract staff Shohan on board date - 7/10 Request staff information - 20/9 Staff ID creation - 21/9 VPN access request - 22/9 | VPN request for new contract staff - Completed | Request staff information - 20/9 Accord Innovations to provide details - 28/9 staff ID creation - 30/9 Portaldom account access - 3/10 Third party form from Accord - 6/10 VPN access request sent to Security - 7/10 Careline cameback with OS patch need to be updated to the latest version, Shohan provided. Sent back to verify - 13/10
Khoon Yong | IAM ID - App Installation | IAM ID - Corona, Murex, FinIQ and FSC installation Approach app team - 22/9 Careline to install - 26/9 Verification - 30/9 | IAM ID - UAT ID request - In progress Pending UAT ID to verify - 3/10 6/10 12/10 14/10 Corona - Received - Testing in progress (Firewall release raised o 13/10. Target to retest on 18/10 FSC - Not received - Pending Mages to provide. | Approach app team - 22/9 FinIQ and FSC able to access via UAT VDI - 26/9 Careline done installation for Corona and Murex - 28/9 Test ID and password FinIQ - Received - Tested Ok Murex - Received - Tested Ok
Khoon Yong | CR171 - Online Activation of Trading Acc - Remove prefix from TradeSmart Client Code | CR171 - Online Activation of Trading Acc - Remove prefix from TradeSmart Client Code Test in UAT for fixes - 27/9 Perform UAT - 28/9 | Online Activation of Trading Account - RCOM submitted. | Environment setup in UAT Perform UAT - 11/10 Perform UAT cycle 2 - 12/10
Khoon Yong | OS upgrade to 21H1 for VDI | OS upgrade to 21H1 is needed. To check on the upgrade is needed or not - 14/10 | Check the upgrade is needed - New To check the upgrade is needed for our end - 14/10

## tracking Consignment
# | item | Description | PIC | Developer | Status | Remarks | Targeted Complition date | Complition Date
1 | Process understanding | Scoping of the process will be performed to understand the feasibility of automation. | Shirly Woo Mei Fong,Nur Juliana Binti Ab Latif,Nur Shazlinda Binti Abdul Halim,Nur Hasyakilla Binti Zainal |  | Done |  | 2023-06-04 | 2023-06-04 |  | status completion timeline | targeted timeline | PIC column
2 | Process Video | It helps to better understand the process. We can see How the user does the manual task. | Nornadia Azhar |  | Done |  | 13/4/2023 | 13/04/2023
3 | Flowchart Creation | We capture the AS-IS process with the help of the user team | Nornadia Azhar |  | Done |  | 17/4/2023 | 17/04/2023
4 | Flowchart Confirmation | The user team approved the flowchart | Shirly Woo Mei Fong,Nur Juliana Binti Ab Latif,Nur Shazlinda Binti Abdul Halim |  | Done |  | 19/4/2023 | 19/04/2023
5 | PDD Creation | Assess functional requirements and perform in-depth analysis of the process. Prepare Process design document. | Nornadia Azhar |  | Done |  | 2023-03-05 | 2023-03-05
6 | PDD Sign-off | The user team goes through, reviews, and approves documents. After that, all stakeholders give the sign-off. | Shirly Woo Mei Fong,Nur Juliana Binti Ab Latif,Nur Shazlinda Binti Abdul Halim |  | Done |  | 2023-05-05 | 2023-09-05
7 | SDD Creation | The solution design document describes how to implement the automated solution | S.M.Shohan |  | Done |  | 2023-09-05 | 24/05/203
8 | SDD Sign-off | All stakeholders need to give the sign of the SDD | Khor Geik Mei,Shirly Woo Mei Fong,Nur Juliana Binti Ab Latif,Nur Shazlinda Binti Abdul Halim |  | Done |  | 2023-10-05 | 31/05/2023
7 | Test Data | Test Data will be required for use in Development | Shirly Woo Mei Fong,Nur Juliana Binti Ab Latif,Nur Shazlinda Binti Abdul Halim,Nur Hasyakilla Binti Zainal,Nornadia Azhar |  | Done |  | 2023-11-05 | 2023-09-05
8 | Development Environment Confirmation | The user team needs to notify which module of the system needs to be accessed. The user team shares the test credentials if it is required. | Shirly Woo Mei Fong,Wong Kok Hong |  | Done |  | 2023-12-05 | 2023-09-05
9 | Development | Develop the automation, Build bots for respective applications, Unit test the bots. | S.M.Shohan |  | in-Progress | start the development on 31/06/2023 Hold development from 02/06/2023 to 09/06/2023 User provided the feedback of summary part and gave new filter criteria for VLE and GLE on 28-Jun-2023 In test environment,there is no data for 2 senario including total amount exceeds 1 M and the PPD,User is creating the test data. | 29/5/2023 30/6/2023 07/7/2023 |  | for exception senario the user need to provide the data-03/07/2023
10 | SIT | Integrate code and perform, System integration testing. | S.M.Shohan |  |  |  | 30/5/2023 30/6/2023 10/7/2023
11 | SIT Sign-off | User give the sign-off | Shirly Woo Mei Fong,Nur Juliana Binti Ab Latif,Nur Shazlinda Binti Abdul Halim |  |  |  | 31/5/2023 04/7/2023 10/7/2023
12 | UAT | End-to-end testing done by the User team. In case of any major defect detected, that need to be fixed | Shirly Woo Mei Fong,Nur Juliana Binti Ab Latif,Nur Shazlinda Binti Abdul Halim,Nornadia Azhar |  | PIC is creating the test data for UAT |  | 6/2/2023 05/7/2023 11/7/2023
13 | UAT Sign-off | User team provide the sign-off | Shirly Woo Mei Fong,Nur Juliana Binti Ab Latif,Nur Shazlinda Binti Abdul Halim |  | Pending |  | 6/5/2023 06/7/2023 12/7/2023 | 2023-07-20
14 | Production Implementation | The process will be implemented in a live environment. | S.M.Shohan |  |  |  | 6/6/2023 07/7/2023 13/7/2023
15 | Production Implementation sign-off | User team provides the sign-off | Shirly Woo Mei Fong,Nur Juliana Binti Ab Latif,Nur Shazlinda Binti Abdul Halim |  |  |  | 6/7/2023 10/7/2023 14/7/2023
15 | Deployment | Deployment of Bot on Live environment | Wong Kok Hong |  |  |  | 6/8/2023 11/7/2023 14/7/2023
16 | Knowledge Transfer | Users will be trained on how to trigger the Bot and maintain configuration files | S.M.Shohan,Nornadia Azhar |  |  |  | 12/7/2023 17/7/2023

## CR-OTC (hidden)
# | Description | PIC | Developer | Status | Remarks | Targeted Complition date | Complition Date
3 | Received source code |  |  | Done |  | 2023-06-19 | 2023-06-19
4 | Discussion with PIC |  |  | Done |  | 2023-06-19 | 2023-06-19
5 | Studying the source code |  |  | Done |  | 2023-06-19 | 2023-06-19
6 | Development |  |  | Done |  | 2023-06-19 | 2023-06-19
7 | Sit |  |  | Done |  | 2023-06-20 | 2023-06-20
8 | UAT |  |  | Done |  | 2023-06-21
9 | UAT sign-off
10 | Deployment

## tracking NT PO Approval (hidden)
# | Description | PIC | Developer | Status | Remarks | Targeted Complition date | Complition Date
1 | Requiermnet Understanding Discussion | Nur Azura Binti Hashim |  | Done |  | 2023-09-05 | 2023-09-05 | status completion timeline | targeted timeline | PIC column
2 | System access and test data | Nur Azura Binti Hashim |  | Done |  | 2023-09-05 | 2023-09-05
4 | Studying the source code | Shohan |  | Done |  | 2023-11-05 | 2023-11-05
5 | Development | Shohan |  | Done | issue faced: 1.Data extraction part of existing code 2.Po Link is not available till 01 may 3.writeoff data for the shared folder file(New scope) | 16/5/2023 | 18/5/2023 02/06/2023
6 | Sit |  |  | Done |  | 17/5/2023 | 18/5/2023
7 | UAT |  |  | in-progress |  | 2023-05-18
8 | UAT sign-off |  |  |  |  | 19/5/2023
9 | Deployment |  |  |  |  | 19/5/2023
22/5/2023
22/5/2023

## Non Trade - Utilities - Gas
# | item | Description | PIC | Developer | Status | Remarks | Baseline due date | Revised Baseline due date | Complition Date
1 | Process understanding | Scoping of the process will be performed to understand the feasibility of automation. |  |  | Done |  | 2/6/2023 |  | 2/6/2023 | status completion timeline | targeted timeline | PIC column
2 | Process Video | It helps to better understand the process. We can see How the user does the manual task. |  |  | Done |  | 13/6/2023 |  | 13/6/2023
3 | Flowchart Creation | We capture the AS-IS process with the help of the user team |  |  | Done |  | 2023-06-16 |  | 2023-06-16
4 | Flowchart Confirmation | The user team approved the flowchart |  |  | Done |  | 2023-06-27 |  | 2023-06-27
5 | PDD Creation | Assess functional requirements and perform in-depth analysis of the process. Prepare Process design document. |  |  | Done |  | 2023-07-04 |  | 2023-07-04
6 | PDD Sign-off | The user team goes through, reviews, and approves documents. After that, all stakeholders give the sign-off. |  |  | Done |  | 5/7/2023 |  | 2023-07-12
7 | SDD Creation | The solution design document describes how to implement the automated solution |  |  | Pending | Aftfer compliton of development will share the sdd | 04/08/2023
8 | SDD Sign-off | All stakeholders need to give the sign of the SDD |  |  | Pending |  | 2023-08-07
7 | Test Data | Test Data will be required for use in Development |  |  | done |  | 2023-08-08
8 | Development Environment Confirmation | The user team needs to notify which module of the system needs to be accessed. The user team shares the test credentials if it is required. |  |  | done |  | 2023-08-08
9 | Development | Develop the automation, Build bots for respective applications, Unit test the bots. |  |  | in-progress | Accrual development in progress | 2023-08-30 | 2023-08-25
10 | SIT | Integrate code and perform, System integration testing. | [5 empty] | 2023-08-28
11 | SIT Sign-off | User give the sign-off
12 | UAT | End-to-end testing done by the User team. In case of any major defect detected, that need to be fixed |  |  |  | require new field to extract from GAS Invoice(LAIN - LAIN CAJ:) | 2023-09-13 | 2023-08-30
13 | UAT Sign-off | User team provide the sign-off |  |  |  |  | 2023-09-14 | 2023-09-01
14 | Production Implementation | The process will be implemented in a live environment. |  |  |  |  | 2023-09-15 | 2023-09-04
15 | Production Implementation sign-off | User team provides the sign-off | [5 empty] | 2023-09-05
15 | Deployment | Deployment of Bot on Live environment |  |  |  |  | 2023-09-15 | 2023-09-05
16 | Knowledge Transfer | Users will be trained on how to trigger the Bot and maintain configuration files |  |  |  |  | 2023-09-14 | 2023-09-06

## Non Trade - Utilities - IDK
# | item | Description | PIC | Developer | Status | Remarks | Baseline due date | Revised Baseline due date | Complition Date
1 | Process understanding | Scoping of the process will be performed to understand the feasibility of automation. |  |  | Done |  | 2/6/2023 |  | 2/6/2023 | status completion timeline | targeted timeline | PIC column
2 | Process Video | It helps to better understand the process. We can see How the user does the manual task. |  |  | Done |  | 13/6/2023 |  | 13/6/2023
3 | Flowchart Creation | We capture the AS-IS process with the help of the user team |  |  | Done |  | 2023-06-16 |  | 2023-06-16
4 | Flowchart Confirmation | The user team approved the flowchart |  |  | Done |  | 2023-06-27 |  | 2023-06-27
5 | PDD Creation | Assess functional requirements and perform in-depth analysis of the process. Prepare Process design document. |  |  | Done |  | 2023-07-04 |  | 2023-07-04
6 | PDD Sign-off | The user team goes through, reviews, and approves documents. After that, all stakeholders give the sign-off. |  |  | Done |  | 5/7/2023 |  | 2023-07-12
7 | SDD Creation | The solution design document describes how to implement the automated solution |  |  | Pending | Aftfer compliton of development will share the sdd | 04/08/2023
8 | SDD Sign-off | All stakeholders need to give the sign of the SDD |  |  | Pending |  | 2023-08-07
7 | Test Data | Test Data will be required for use in Development |  |  | done |  | 2023-08-08
8 | Development Environment Confirmation | The user team needs to notify which module of the system needs to be accessed. The user team shares the test credentials if it is required. |  |  | done |  | 2023-08-08
9 | Development | Develop the automation, Build bots for respective applications, Unit test the bots. |  |  | in-progress | Accrual development in progress | 2023-09-17
10 | SIT | Integrate code and perform, System integration testing.
11 | SIT Sign-off | User give the sign-off
12 | UAT | End-to-end testing done by the User team. In case of any major defect detected, that need to be fixed |  |  |  |  | 2023-09-18
13 | UAT Sign-off | User team provide the sign-off |  |  |  |  | 2023-09-19
14 | Production Implementation | The process will be implemented in a live environment. |  |  |  |  | 2023-09-20
15 | Production Implementation sign-off | User team provides the sign-off
15 | Deployment | Deployment of Bot on Live environment |  |  |  |  | 2023-09-21
16 | Knowledge Transfer | Users will be trained on how to trigger the Bot and maintain configuration files

## Non Trade - Utilities - Time
# | item | Description | PIC | Developer | Status | Remarks | Baseline due date | Revised Baseline due date | Complition Date
1 | Process understanding | Scoping of the process will be performed to understand the feasibility of automation. |  |  | Done |  | 2/6/2023 |  | 2/6/2023 | status completion timeline | targeted timeline | PIC column
2 | Process Video | It helps to better understand the process. We can see How the user does the manual task. |  |  | Done |  | 13/6/2023 |  | 13/6/2023
3 | Flowchart Creation | We capture the AS-IS process with the help of the user team |  |  | Done |  | 2023-06-16 |  | 2023-06-16
4 | Flowchart Confirmation | The user team approved the flowchart |  |  | Done |  | 2023-06-27 |  | 2023-06-27
5 | PDD Creation | Assess functional requirements and perform in-depth analysis of the process. Prepare Process design document. |  |  | Done |  | 2023-07-04 |  | 2023-07-04
6 | PDD Sign-off | The user team goes through, reviews, and approves documents. After that, all stakeholders give the sign-off. |  |  | Done |  | 5/7/2023 |  | 2023-07-12
7 | SDD Creation | The solution design document describes how to implement the automated solution |  |  | Pending | Aftfer compliton of development will share the sdd | 04/08/2023
8 | SDD Sign-off | All stakeholders need to give the sign of the SDD |  |  | Pending |  | 2023-08-07
7 | Test Data | Test Data will be required for use in Development |  |  | done |  | 2023-08-08
8 | Development Environment Confirmation | The user team needs to notify which module of the system needs to be accessed. The user team shares the test credentials if it is required. |  |  | done |  | 2023-08-08
9 | Development | Develop the automation, Build bots for respective applications, Unit test the bots. |  |  | in-progress | Accrual development in progress | 2023-09-18
10 | SIT | Integrate code and perform, System integration testing.
11 | SIT Sign-off | User give the sign-off
12 | UAT | End-to-end testing done by the User team. In case of any major defect detected, that need to be fixed |  |  |  |  | 2023-09-20
13 | UAT Sign-off | User team provide the sign-off |  |  |  |  | 2023-09-21
14 | Production Implementation | The process will be implemented in a live environment. |  |  |  |  | 2023-09-22
15 | Production Implementation sign-off | User team provides the sign-off
15 | Deployment | Deployment of Bot on Live environment |  |  |  |  | 2023-09-25
16 | Knowledge Transfer | Users will be trained on how to trigger the Bot and maintain configuration files

## Non Trade - Utilities - TNB
# | item | Description | PIC | Developer | Status | Remarks | Baseline due date | Revised Baseline due date | Complition Date
1 | Process understanding | Scoping of the process will be performed to understand the feasibility of automation. |  |  | Done |  | 2/6/2023 |  | 2/6/2023 | status completion timeline | targeted timeline | PIC column
2 | Process Video | It helps to better understand the process. We can see How the user does the manual task. |  |  | Done |  | 13/6/2023 |  | 13/6/2023
3 | Flowchart Creation | We capture the AS-IS process with the help of the user team |  |  | Done |  | 2023-06-16 |  | 2023-06-16
4 | Flowchart Confirmation | The user team approved the flowchart |  |  | Done |  | 2023-06-27 |  | 2023-06-27
5 | PDD Creation | Assess functional requirements and perform in-depth analysis of the process. Prepare Process design document. |  |  | Done |  | 2023-07-04 |  | 2023-07-04
6 | PDD Sign-off | The user team goes through, reviews, and approves documents. After that, all stakeholders give the sign-off. |  |  | Done |  | 5/7/2023 |  | 2023-07-12
7 | SDD Creation | The solution design document describes how to implement the automated solution |  |  | Pending | Aftfer compliton of development will share the sdd | 04/08/2023
8 | SDD Sign-off | All stakeholders need to give the sign of the SDD |  |  | Pending |  | 2023-08-07
7 | Test Data | Test Data will be required for use in Development |  |  | done |  | 2023-08-08
8 | Development Environment Confirmation | The user team needs to notify which module of the system needs to be accessed. The user team shares the test credentials if it is required. |  |  | done |  | 2023-08-08
9 | Development | Develop the automation, Build bots for respective applications, Unit test the bots. |  |  | in-progress | Accrual development in progress | 2023-08-30 | 2023-08-25
10 | SIT | Integrate code and perform, System integration testing. | [5 empty] | 2023-08-28
11 | SIT Sign-off | User give the sign-off
12 | UAT | End-to-end testing done by the User team. In case of any major defect detected, that need to be fixed |  |  |  |  | 2023-09-05 | 2023-08-30
13 | UAT Sign-off | User team provide the sign-off |  |  |  |  | 2023-09-06 | 2023-09-01
14 | Production Implementation | The process will be implemented in a live environment. |  |  |  |  | 2023-09-11 | 2023-09-04
15 | Production Implementation sign-off | User team provides the sign-off | [5 empty] | 2023-09-05
15 | Deployment | Deployment of Bot on Live environment |  |  |  |  | 2023-09-13 | 2023-09-05
16 | Knowledge Transfer | Users will be trained on how to trigger the Bot and maintain configuration files |  |  |  |  | 2023-09-14 | 2023-09-06

## Non Trade - Utilities - Celcom
# | item | Description | PIC | Developer | Status | Remarks | Baseline due date | Revised Baseline due date | Complition Date
1 | Process understanding | Scoping of the process will be performed to understand the feasibility of automation. |  |  | Done |  | 2/6/2023 |  | 2/6/2023 | status completion timeline | targeted timeline | PIC column
2 | Process Video | It helps to better understand the process. We can see How the user does the manual task. |  |  | Done |  | 13/6/2023 |  | 13/6/2023
3 | Flowchart Creation | We capture the AS-IS process with the help of the user team |  |  | Done |  | 2023-06-16 |  | 2023-06-16
4 | Flowchart Confirmation | The user team approved the flowchart |  |  | Done |  | 2023-06-27 |  | 2023-06-27
5 | PDD Creation | Assess functional requirements and perform in-depth analysis of the process. Prepare Process design document. |  |  | Done |  | 2023-07-04 |  | 2023-07-04
6 | PDD Sign-off | The user team goes through, reviews, and approves documents. After that, all stakeholders give the sign-off. |  |  | Done |  | 5/7/2023 |  | 2023-07-12
7 | SDD Creation | The solution design document describes how to implement the automated solution |  |  | Pending | Aftfer compliton of development will share the sdd | 04/08/2023
8 | SDD Sign-off | All stakeholders need to give the sign of the SDD |  |  | Pending |  | 2023-08-07
7 | Test Data | Test Data will be required for use in Development |  |  | done |  | 2023-08-08
8 | Development Environment Confirmation | The user team needs to notify which module of the system needs to be accessed. The user team shares the test credentials if it is required. |  |  | done |  | 2023-08-08
9 | Development | Develop the automation, Build bots for respective applications, Unit test the bots. |  |  | in-progress | Accrual development in progress | 2023-08-30 | 2023-08-25
10 | SIT | Integrate code and perform, System integration testing. | [5 empty] | 2023-08-28
11 | SIT Sign-off | User give the sign-off
12 | UAT | End-to-end testing done by the User team. In case of any major defect detected, that need to be fixed |  |  |  |  | 2023-09-05 | 2023-08-30
13 | UAT Sign-off | User team provide the sign-off |  |  |  |  | 2023-09-06 | 2023-09-01
14 | Production Implementation | The process will be implemented in a live environment. |  |  |  |  | 2023-09-11 | 2023-09-04
15 | Production Implementation sign-off | User team provides the sign-off | [5 empty] | 2023-09-05
15 | Deployment | Deployment of Bot on Live environment |  |  |  |  | 2023-09-13 | 2023-09-05
16 | Knowledge Transfer | Users will be trained on how to trigger the Bot and maintain configuration files |  |  |  |  | 2023-09-14 | 2023-09-06

## Non Trade - Utilities - TM
# | item | Description | PIC | Developer | Status | Remarks | Baseline due date | Revised Baseline due date | Complition Date
1 | Process understanding | Scoping of the process will be performed to understand the feasibility of automation. |  |  | Done |  | 2/6/2023 |  | 2/6/2023 | status completion timeline | targeted timeline | PIC column
2 | Process Video | It helps to better understand the process. We can see How the user does the manual task. |  |  | Done |  | 13/6/2023 |  | 13/6/2023
3 | Flowchart Creation | We capture the AS-IS process with the help of the user team |  |  | Done |  | 2023-06-16 |  | 2023-06-16
4 | Flowchart Confirmation | The user team approved the flowchart |  |  | Done |  | 2023-06-27 |  | 2023-06-27
5 | PDD Creation | Assess functional requirements and perform in-depth analysis of the process. Prepare Process design document. |  |  | Done |  | 2023-07-04 |  | 2023-07-04
6 | PDD Sign-off | The user team goes through, reviews, and approves documents. After that, all stakeholders give the sign-off. |  |  | Done |  | 5/7/2023 |  | 2023-07-12
7 | SDD Creation | The solution design document describes how to implement the automated solution |  |  | Pending | Aftfer compliton of development will share the sdd | 04/08/2023
8 | SDD Sign-off | All stakeholders need to give the sign of the SDD |  |  | Pending |  | 2023-08-07
7 | Test Data | Test Data will be required for use in Development |  |  | done |  | 2023-08-08
8 | Development Environment Confirmation | The user team needs to notify which module of the system needs to be accessed. The user team shares the test credentials if it is required. |  |  | done |  | 2023-08-08
9 | Development | Develop the automation, Build bots for respective applications, Unit test the bots. |  |  | in-progress | Accrual development in progress | 2023-08-30 | 2023-08-25
10 | SIT | Integrate code and perform, System integration testing. | [5 empty] | 2023-08-28
11 | SIT Sign-off | User give the sign-off
12 | UAT | End-to-end testing done by the User team. In case of any major defect detected, that need to be fixed |  |  |  |  | 2023-09-05 | 2023-08-30
13 | UAT Sign-off | User team provide the sign-off |  |  |  |  | 2023-09-06 | 2023-09-01
14 | Production Implementation | The process will be implemented in a live environment. |  |  |  |  | 2023-09-11 | 2023-09-04
15 | Production Implementation sign-off | User team provides the sign-off | [5 empty] | 2023-09-05
15 | Deployment | Deployment of Bot on Live environment |  |  |  |  | 2023-09-13 | 2023-09-05
16 | Knowledge Transfer | Users will be trained on how to trigger the Bot and maintain configuration files |  |  |  |  | 2023-09-14 | 2023-09-06

## Non Trade - Utilities - Syabas
# | item | Description | PIC | Developer | Status | Remarks | Baseline due date | Revised Baseline due date | Complition Date
1 | Process understanding | Scoping of the process will be performed to understand the feasibility of automation. |  |  | Done |  | 2/6/2023 |  | 2/6/2023 | status completion timeline | targeted timeline | PIC column
2 | Process Video | It helps to better understand the process. We can see How the user does the manual task. |  |  | Done |  | 13/6/2023 |  | 13/6/2023
3 | Flowchart Creation | We capture the AS-IS process with the help of the user team |  |  | Done |  | 2023-06-16 |  | 2023-06-16
4 | Flowchart Confirmation | The user team approved the flowchart |  |  | Done |  | 2023-06-27 |  | 2023-06-27
5 | PDD Creation | Assess functional requirements and perform in-depth analysis of the process. Prepare Process design document. |  |  | Done |  | 2023-07-04 |  | 2023-07-04
6 | PDD Sign-off | The user team goes through, reviews, and approves documents. After that, all stakeholders give the sign-off. |  |  | Done |  | 5/7/2023 |  | 2023-07-12
7 | SDD Creation | The solution design document describes how to implement the automated solution |  |  | Pending | Aftfer compliton of development will share the sdd | 04/08/2023
8 | SDD Sign-off | All stakeholders need to give the sign of the SDD |  |  | Pending |  | 2023-08-07
7 | Test Data | Test Data will be required for use in Development |  |  | done |  | 2023-08-08
8 | Development Environment Confirmation | The user team needs to notify which module of the system needs to be accessed. The user team shares the test credentials if it is required. |  |  | done |  | 2023-08-08
9 | Development | Develop the automation, Build bots for respective applications, Unit test the bots. |  |  | in-progress | Accrual development in progress | 2023-08-30 | 2023-08-25
10 | SIT | Integrate code and perform, System integration testing. | [5 empty] | 2023-08-28
11 | SIT Sign-off | User give the sign-off
12 | UAT | End-to-end testing done by the User team. In case of any major defect detected, that need to be fixed |  |  |  |  | 2023-09-05 | 2023-08-30
13 | UAT Sign-off | User team provide the sign-off |  |  |  |  | 2023-09-06 | 2023-09-01
14 | Production Implementation | The process will be implemented in a live environment. |  |  |  |  | 2023-09-11 | 2023-09-04
15 | Production Implementation sign-off | User team provides the sign-off | [5 empty] | 2023-09-05
15 | Deployment | Deployment of Bot on Live environment |  |  |  |  | 2023-09-13 | 2023-09-05
16 | Knowledge Transfer | Users will be trained on how to trigger the Bot and maintain configuration files |  |  |  |  | 2023-09-14 | 2023-09-06

## Central Ordering
# | item | Description | PIC | Developer | Status | Remarks | Baseline due date | Revised Baseline due date | Complition Date
1 | Process understanding | Scoping of the process will be performed to understand the feasibility of automation. | Yap Shang Shin |  | Done |  | 11/9/2023 | 2023-09-11 |  | status completion timeline | targeted timeline | PIC column
2 | Process Video | It helps to better understand the process. We can see How the user does the manual task. | Yap Shang Shin |  | Done |  | 04/9/2023 | 2023-09-04
3 | Flowchart Creation | We capture the AS-IS process with the help of the user team | Yap Shang Shin |  | Done |  | 04/9/2023 | 2023-09-04
4 | Flowchart Confirmation | The user team approved the flowchart | Yap Shang Shin |  | Done |  | 04/9/2023 | 2023-09-04
5 | PDD Creation | Assess functional requirements and perform in-depth analysis of the process. Prepare Process design document. | Yap Shang Shin |  | Done |  | 04/9/2023 | 2023-09-04
6 | PDD Sign-off | The user team goes through, reviews, and approves documents. After that, all stakeholders give the sign-off. |  |  | pending
7 | SDD Creation | The solution design document describes how to implement the automated solution |  |  | Pending | After compliton of development will share the sdd
8 | SDD Sign-off | All stakeholders need to give the sign of the SDD |  |  | Pending
7 | Test Data | Test Data will be required for use in Development |  |  | Done |  | 2023-09-14
8 | Development Environment Confirmation | The user team needs to notify which module of the system needs to be accessed. The user team shares the test credentials if it is required. |  |  | Pending |  | 2023-09-15
9 | Development | Develop the automation, Build bots for respective applications, Unit test the bots. |  |  | Done | Actual development in progress | 2023-10-05
| Development Sub Process 1: Login To LS System, Download Retail Vendor List, Item Status Link, Item Master List and Replen. Item Quanlity Files. | Login the LS system, Download all required files, give proper filter and get the excel |  |  | Development Done, UAT Done, Signedoff | BOT Installation on user computer done. And Started Using on Prod Environment.
| Development Sub Process 2: Get Promotion File for Combining Data. Prepare Uploading Excel Sheet to LS System. | Promotion file from Merchandising Department on a shared folder, updated Staff Directory on the shared folder and all Downloaded Files form the LS system. Combining all files with proper logic and calculations,prepare the sheet for uploading to the system |  |  | Development done. UAT IN PROGRESS | BOT Installation on user computer done.User is checking after changed request changes are done.
| Sub Processs 1 & 2 Sign Off From User | The User team needs to sign-off the sub process result after accessing the result. They manually check the result and give sign-off upon everything is ok.
| Development Sub Process 3: Upload all the from the Excel Sheet to LS sytem. | This process uploads all the data into the LS system from the signed-off excel file. |  |  | Development Done,UAT DONE | Bot Installation done.
10 | SIT | Integrate code and perform, System integration testing. |  |  | Integration to LS system done |  | 2023-10-10
11 | SIT Sign-off | User give the sign-off |  |  |  |  | 2023-10-10
12 | UAT | End-to-end testing done by the User team. In case of any major defect detected, that need to be fixed |  |  | ONLY SUBPROCESS 2 |  | 2023-10-11
13 | UAT Sign-off | User team provide the sign-off |  |  | Partial |  | 2023-10-12
14 | Production Implementation | The process will be implemented in a live environment. |  |  | Full |  | 2023-10-17
15 | Production Implementation sign-off | User team provides the sign-off |  |  |  |  | 2023-10-18
15 | Deployment | Deployment of Bot on Live environment |  |  | As per user request partial process was deployed, Posting to LS is not done yet. |  | 2023-10-20
16 | Knowledge Transfer | Users will be trained on how to trigger the Bot and maintain configuration files |  |  | Done, Gave User document which includes all information how to run the bot, Instructions and Prerequisits |  | 2023-10-21